## JOSE ANTONY MUTHU
NSURE Motor Policy Inssuance System
S.no | Name | Date | Time | Project Task | Status
1 | Jose Antony Muthu S | 11.12.2017 | 10:45 AM to 4:00 PM | Absent
2 | Jose Antony Muthu S | 12.12.2017 | 10:45 AM to 4:00 PM | Absent
3 | Jose Antony Muthu S | 13.12.2017 | 10:45 AM to 4:00 PM | Absent
4 | Jose Antony Muthu S | 14.12.2017 | 10:45 AM to 4:00 PM | Zeroth Review
5 | Jose Antony Muthu S | 15.12.2017 | 10:45 AM to 4:00 PM | Installing and Configuring Development Tool | Completed
|  | Saturday |  | Holiday
Sunday
6 | Jose Antony Muthu S | 18.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Angular JS | Completed
7 | Jose Antony Muthu S | 19.12.2017 | 10:45 AM to 4:00 PM | Absent
8 | Jose Antony Muthu S | 20.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Spring Framework | Completed
9 | Jose Antony Muthu S | 21.12.2017 | 10:45 AM to 4:00 PM | Absent
10 | Jose Antony Muthu S | 22.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
|  | Saturday |  | Holiday
Sunday
Monday
11 | Jose Antony Muthu S | 26.12.2017 | 10:45 AM to 4:00 PM | Absent
12 | Jose Antony Muthu S | 27.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
13 | Jose Antony Muthu S | 28.12.2017 | 10:45 AM to 4:00 PM | Learning Angular Js and Spring Framework | Completed
14 | Jose Antony Muthu S | 29.12.2017 | 10:45 AM to 4:00 PM | Absent(placement drive)
15 | Jose Antony Muthu S | 30.12.2017 | 10:45 AM to 4:00 PM | Absent
|  | Sunday |  | Holiday
Monday
16 | Jose Antony Muthu S | 02.01.2018 | 10:45 AM to 4:00 PM | Absent
17 | Jose Antony Muthu S | 03.01.2018 | 10:45 AM to 4:00 PM | UI Design-Module 1 | Completed
18 | Jose Antony Muthu S | 04.01.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
19 | Jose Antony Muthu S | 05.01.2018 | 10:45 AM to 4:00 PM | Absent
|  | Saturday |  | Holiday
Sunday
20 | Jose Antony Muthu S | 08.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 1 | Completed
21 | Jose Antony Muthu S | 09.01.2018 | 10:45 AM to 4:00 PM | Learning ireport | Completed
22 | Jose Antony Muthu S | 10.01.2018 | 10:45 AM to 4:00 PM | Working on Sample ireport | Completed
23 | Jose Antony Muthu S | 11.01.2018 | 10:45 AM to 4:00 PM | JDBC connectivity in iReports | Completed
Holiday
24 | Jose Antony Muthu S | 17.01.2018 | 10:45 AM to 4:00 PM | Generating iReports | Completed
25 | Jose Antony Muthu S | 18.01.2018 | 10:45 AM to 4:00 PM | First Review
26 | Jose Antony Muthu S | 19.01.2018 | 10:45 AM to 4:00 PM | Learning JSON | Completed
27 | Jose Antony Muthu S | 20.01.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
|  | Sunday |  | Holiday
28 | Jose Antony Muthu S | 22.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 2 | In Progress
29 | Jose Antony Muthu S | 23.01.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
30 | Jose Antony Muthu S | 24.01.2018 | 10:45 AM to 4:00 PM | Absent
31 | Jose Antony Muthu S | 25.01.2018 | 10:45 AM to 4:00 PM | Spring JDBC Connection | Completed
|  | Friday |  | Holiday
Saturday
Sunday
32 | Jose Antony Muthu S | 29.01.2018 | 10:45 AM to 4:00 PM | Generating iReports | Completed
33 | Jose Antony Muthu S | 30.01.2018 | 10:45 AM to 4:00 PM | Generating iReports | Completed
34 | Jose Antony Muthu S | 31.01.2018 | 10:45 AM to 4:00 PM | Learning JSON | Completed
35 | Jose Antony Muthu S | 01.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
36 | Jose Antony Muthu S | 02.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
37 | Jose Antony Muthu S | 03.02.2018 | 10:45 AM to 4:00 PM | Absent
|  | Sunday |  | Holiday
38 | Jose Antony Muthu S | 05.02.2018 | 10:45 AM to 4:00 PM | Schedule print generation | In Progress
39 | Jose Antony Muthu S | 06.02.2018 | 10:45 AM to 4:00 PM | Schedule print generation | In Progress
40 | Jose Antony Muthu S | 07.02.2018 | 10:45 AM to 4:00 PM | Schedule print generation | In Progress
41 | Jose Antony Muthu S | 08.02.2018 | 10:45 AM to 4:00 PM | iReport and spring integration | In Progress
42 | Jose Antony Muthu S | 09.02.2018 | 10:45 AM to 4:00 PM | iReport and spring integration | In Progress
43 | Jose Antony Muthu S | 10.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
|  | Sunday |  | Holiday
44 | Jose Antony Muthu S | 12.02.2018 | 10:45 AM to 4:00 PM | iReport and spring integration | In Progress
45 | Jose Antony Muthu S | 13.02.2018 | 10:45 AM to 4:00 PM | Spring MVC PDF Generation | In Progress
46 | Jose Antony Muthu S | 14.02.2018 | 10:45 AM to 4:00 PM | Spring MVC PDF Generation | In Progress
47 | Jose Antony Muthu S | 15.02.2018 | 10:45 AM to 4:00 PM | Spring MVC PDF Generation | In Progress
48 | Jose Antony Muthu S | 16.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
49 | Jose Antony Muthu S | 17.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
|  | Sunday |  | Holiday
50 | Jose Antony Muthu S | 19.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
51 | Jose Antony Muthu S | 20.02.2018 | 10:45 AM to 4:00 PM | Spring MVC PDF Generation | In Progress
52 | Jose Antony Muthu S | 21.02.2018 | 10:45 AM to 4:00 PM | Spring MVC PDF Generation | In Progress
53 | Jose Antony Muthu S | 22.02.2018 | 10:45 AM to 4:00 PM | Spring MVC PDF Generation | In Progress
54 | Jose Antony Muthu S | 23.02.2018 | 10:45 AM to 4:00 PM | Spring MVC PDF Generation | In Progress
|  | Saturday |  | Holiday
Sunday
55 | Jose Antony Muthu S | 26.02.2018 | 10:45 AM to 4:00 PM | iReport and spring integration | In Progress
56 | Jose Antony Muthu S | 27.02.2018 | 10:45 AM to 4:00 PM | Second review
57 | Jose Antony Muthu S | 28.02.2018 | 10:45 AM to 4:00 PM | Second review
58 | Jose Antony Muthu S | 01.03.2018 | 10:45 AM to 4:00 PM | Jasper ireport | In Progress
59 | Jose Antony Muthu S | 02.03.2018 | 10:45 AM to 4:00 PM | Jasper ireport | In Progress
60 | Jose Antony Muthu S | 03.03.2018 | 10:45 AM to 4:00 PM | Jasper ireport | In Progress
|  | Sunday |  | Holiday
61 | Jose Antony Muthu S | 05.03.2018 | 10:45 AM to 4:00 PM | Jasper ireport | In Progress

## AKSHAYA
NSURE Motor Policy Inssuance System
S.no | Name | Date | Time | Project Task | Status
1 | Akshaya M | 11.12.2017 | 10:45 AM to 4:00 PM | Domain knowledge | Completed
2 | Akshaya M | 12.12.2017 | 10:45 AM to 4:00 PM | Domain knowledge | Completed
3 | Akshaya M | 13.12.2017 | 10:45 AM to 4:00 PM | Refreshing Basics Java | Completed
4 | Akshaya M | 14.12.2017 | 10:45 AM to 4:00 PM | Zeroth Review
5 | Akshaya M | 15.12.2017 | 10:45 AM to 4:00 PM | Installing and Configuring Development Tool | Completed
|  | Saturday |  | Holiday
Sunday
6 | Akshaya M | 18.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Angular JS | Completed
7 | Akshaya M | 19.12.2017 | 10:45 AM to 4:00 PM | Executing Sample Java Project | Completed
8 | Akshaya M | 20.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Spring Framework | Completed
9 | Akshaya M | 21.12.2017 | 10:45 AM to 4:00 PM | Absent
10 | Akshaya M | 22.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
|  | Saturday |  | Holiday
Sunday
Monday
11 | Akshaya M | 26.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
12 | Akshaya M | 27.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
13 | Akshaya M | 28.12.2017 | 10:45 AM to 4:00 PM | Absent
14 | Akshaya M | 29.12.2017 | 10:45 AM to 4:00 PM | Absent(placement drive)
15 | Akshaya M | 30.12.2017 | 10:45 AM to 4:00 PM | Absent
|  | Sunday |  | Holiday
Monday
16 | Akshaya M | 02.01.2018 | 10:45 AM to 4:00 PM | Grid UI design | Completed
17 | Akshaya M | 03.01.2018 | 10:45 AM to 4:00 PM | UI Design-Module 1 | Completed
18 | Akshaya M | 04.01.2018 | 10:45 AM to 4:00 PM | UI Design-Module 1 | Completed
19 | Akshaya M | 05.01.2018 | 10:45 AM to 4:00 PM | UI Design-Module 1 | Completed
|  | Saturday |  | Holiday
Sunday
20 | Akshaya M | 08.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 1 | Completed
21 | Akshaya M | 09.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 1 | Completed
22 | Akshaya M | 10.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 1 | In Progress
23 | Akshaya M | 11.01.2018 | 10:45 AM to 4:00 PM | UI Design -Module 3 | Completed
Holiday
24 | Akshaya M | 17.01.2018 | 10:45 AM to 4:00 PM | UI Design -Module 3 | In Progress
25 | Akshaya M | 18.01.2018 | 10:45 AM to 4:00 PM | First Review
26 | Akshaya M | 19.01.2018 | 10:45 AM to 4:00 PM | UI Design -Module 3 | In Progress
27 | Akshaya M | 20.01.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
|  | Sunday |  | Holiday
28 | Akshaya M | 22.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 2 | Completed
29 | Akshaya M | 23.01.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
30 | Akshaya M | 24.01.2018 | 10:45 AM to 4:00 PM | Absent
31 | Akshaya M | 25.01.2018 | 10:45 AM to 4:00 PM | Spring JDBC Connection | Completed
|  | Friday |  | Holiday
Saturday
Sunday
32 | Akshaya M | 29.01.2018 | 10:45 AM to 4:00 PM | Learning JSON | Completed
33 | Akshaya M | 30.01.2018 | 10:45 AM to 4:00 PM | Learning JSON | Completed
34 | Akshaya M | 31.01.2018 | 10:45 AM to 4:00 PM | Learning JSON | Completed
35 | Akshaya M | 01.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
36 | Akshaya M | 02.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
37 | Akshaya M | 03.02.2018 | 10:45 AM to 4:00 PM | Absent
|  | Sunday |  | Holiday
38 | Akshaya M | 05.02.2018 | 10:45 AM to 4:00 PM | Master table creation | In Progress
39 | Akshaya M | 06.02.2018 | 10:45 AM to 4:00 PM | Master table creation | In Progress
40 | Akshaya M | 07.02.2018 | 10:45 AM to 4:00 PM | Master table creation | In Progress
41 | Akshaya M | 08.02.2018 | 10:45 AM to 4:00 PM | Master table creation | In Progress
42 | Akshaya M | 09.02.2018 | 10:45 AM to 4:00 PM | Master table creation | In Progress
43 | Akshaya M | 10.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
|  | Sunday |  | Holiday
44 | Akshaya M | 12.02.2018 | 10:45 AM to 4:00 PM | Angular Js and Form validation | In Progress
45 | Akshaya M | 13.02.2018 | 10:45 AM to 4:00 PM | Module3-UI grid | In Progress
46 | Akshaya M | 14.02.2018 | 10:45 AM to 4:00 PM | Module3-UI grid | In Progress
47 | Akshaya M | 15.02.2018 | 10:45 AM to 4:00 PM | Module3-UI grid | In Progress
48 | Akshaya M | 16.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
49 | Akshaya M | 17.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
Sunday
50 | Akshaya M | 19.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
51 | Akshaya M | 20.02.2018 | 10:45 AM to 4:00 PM | Module3-UI grid | In Progress
52 | Akshaya M | 21.02.2018 | 10:45 AM to 4:00 PM | Module3-UI grid | In Progress
53 | Akshaya M | 22.02.2018 | 10:45 AM to 4:00 PM | Module3-UI grid | In Progress
54 | Akshaya M | 23.02.2018 | 10:45 AM to 4:00 PM | Module3-UI grid | In Progress
|  | Saturday |  | Holiday
Sunday
55 | Akshaya M | 26.02.2018 | 10:45 AM to 4:00 PM | Module3-UI grid | In Progress
56 | Akshaya M | 27.02.2018 | 10:45 AM to 4:00 PM | Second review
57 | Akshaya M | 28.02.2018 | 10:45 AM to 4:00 PM | Second review
58 | Akshaya M | 01.03.2018 | 10:45 AM to 4:00 PM | Module3-UI grid | In Progress
59 | Akshaya M | 02.03.2018 | 10:45 AM to 4:00 PM | Module3-UI grid | In Progress
60 | Akshaya M | 03.03.2018 | 10:45 AM to 4:00 PM | Absent | In Progress
|  | Sunday |  | Holiday
61 | Akshaya M | 05.03.2018 | 10:45 AM to 4:00 PM | Database table creation | In Progress

## MOHANAKRISHNAN
NSURE Motor Policy Inssuance System
S.no | Name | Date | Time | Project Task | Status
1 | Mohana Krishnan S | 11.12.2017 | 10:45 AM to 4:00 PM | Domain knowledge | Completed
2 | Mohana Krishnan S | 12.12.2017 | 10:45 AM to 4:00 PM | Domain knowledge | Completed
3 | Mohana Krishnan S | 13.12.2017 | 10:45 AM to 4:00 PM | Refreshing Basics Java | Completed
4 | Mohana Krishnan S | 14.12.2017 | 10:45 AM to 4:00 PM | Zeroth Review
5 | Mohana Krishnan S | 15.12.2017 | 10:45 AM to 4:00 PM | Installing and Configuring Development Tool | Completed
|  | Saturday |  | Holiday
Sunday
6 | Mohana Krishnan S | 18.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Angular JS | Completed
7 | Mohana Krishnan S | 19.12.2017 | 10:45 AM to 4:00 PM | Executing Sample Java Project | Completed
8 | Mohana Krishnan S | 20.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Spring Framework | Completed
9 | Mohana Krishnan S | 21.12.2017 | 10:45 AM to 4:00 PM | Absent
10 | Mohana Krishnan S | 22.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
|  | Saturday |  | Holiday
Sunday
Monday
11 | Mohana Krishnan S | 26.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
12 | Mohana Krishnan S | 27.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
13 | Mohana Krishnan S | 28.12.2017 | 10:45 AM to 4:00 PM | Learning Angular Js and Spring Framework | Completed
14 | Mohana Krishnan S | 29.12.2017 | 10:45 AM to 4:00 PM | Absent(placement drive)
15 | Mohana Krishnan S | 30.12.2017 | 10:45 AM to 4:00 PM | Absent
|  | Sunday |  | Holiday
Monday
16 | Mohana Krishnan S | 02.01.2018 | 10:45 AM to 4:00 PM | Grid UI design | Completed
17 | Mohana Krishnan S | 03.01.2018 | 10:45 AM to 4:00 PM | UI Design-Module 1 | Completed
18 | Mohana Krishnan S | 04.01.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
19 | Mohana Krishnan S | 05.01.2018 | 10:45 AM to 4:00 PM | UI Design-Module 1 | Completed
|  | Saturday |  | Holiday
Sunday
20 | Mohana Krishnan S | 08.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 1 | Completed
21 | Mohana Krishnan S | 09.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 1 | Completed
22 | Mohana Krishnan S | 10.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 1 | In Progress
23 | Mohana Krishnan S | 11.01.2018 | 10:45 AM to 4:00 PM | Dashboard controls | Completed
Holiday
24 | Mohana Krishnan S | 17.01.2018 | 10:45 AM to 4:00 PM | Dashboard controls | Completed
25 | Mohana Krishnan S | 18.01.2018 | 10:45 AM to 4:00 PM | Dashboard controls | Completed
26 | Mohana Krishnan S | 19.01.2018 | 10:45 AM to 4:00 PM | Dashboard controls | Completed
27 | Mohana Krishnan S | 20.01.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
|  | Sunday |  | Holiday
28 | Mohana Krishnan S | 22.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 2 | Completed
29 | Mohana Krishnan S | 23.01.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
30 | Mohana Krishnan S | 24.01.2018 | 10:45 AM to 4:00 PM | Spring JDBC Connection | Completed
31 | Mohana Krishnan S | 25.01.2018 | 10:45 AM to 4:00 PM | Spring JDBC Connection | Completed
|  | Friday |  | Holiday
Saturday
Sunday
32 | Mohana Krishnan S | 29.01.2018 | 10:45 AM to 4:00 PM | Learning JSON | Completed
33 | Mohana Krishnan S | 30.01.2018 | 10:45 AM to 4:00 PM | Learning JSON | Completed
34 | Mohana Krishnan S | 31.01.2018 | 10:45 AM to 4:00 PM | Learning JSON | Completed
35 | Mohana Krishnan S | 01.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
36 | Mohana Krishnan S | 02.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
37 | Mohana Krishnan S | 03.02.2018 | 10:45 AM to 4:00 PM | Absent
|  | Sunday |  | Holiday
38 | Mohana Krishnan S | 05.02.2018 | 10:45 AM to 4:00 PM | Angular Js and Form validation | In Progress
39 | Mohana Krishnan S | 06.02.2018 | 10:45 AM to 4:00 PM | Angular Js and Form validation | In Progress
40 | Mohana Krishnan S | 07.02.2018 | 10:45 AM to 4:00 PM | Angular Js and Form validation | In Progress
41 | Mohana Krishnan S | 08.02.2018 | 10:45 AM to 4:00 PM | Angular Js and Form validation | In Progress
42 | Mohana Krishnan S | 09.02.2018 | 10:45 AM to 4:00 PM | Angular Js and Form validation | In Progress
43 | Mohana Krishnan S | 10.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
|  | Sunday |  | Holiday
44 | Mohana Krishnan S | 12.02.2018 | 10:45 AM to 4:00 PM | Angular Js and Form validation | In Progress
45 | Mohana Krishnan S | 13.02.2018 | 10:45 AM to 4:00 PM | Dashboard controls | In Progress
46 | Mohana Krishnan S | 14.02.2018 | 10:45 AM to 4:00 PM | Dashboard controls | In Progress
47 | Mohana Krishnan S | 15.02.2018 | 10:45 AM to 4:00 PM | Dashboard controls | In Progress
48 | Mohana Krishnan S | 16.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
49 | Mohana Krishnan S | 17.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
Sunday
50 | Mohana Krishnan S | 19.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
51 | Mohana Krishnan S | 20.02.2018 | 10:45 AM to 4:00 PM | Procedure writing | In Progress
52 | Mohana Krishnan S | 21.02.2018 | 10:45 AM to 4:00 PM | Procedure writing | In Progress
53 | Mohana Krishnan S | 22.02.2018 | 10:45 AM to 4:00 PM | Procedure writing | In Progress
54 | Mohana Krishnan S | 23.02.2018 | 10:45 AM to 4:00 PM | Procedure writing | In Progress
|  | Saturday |  | Holiday
Sunday
55 | Mohana Krishnan S | 26.02.2018 | 10:45 AM to 4:00 PM | UI grid | In Progress
56 | Mohana Krishnan S | 27.02.2018 | 10:45 AM to 4:00 PM | Second review
57 | Mohana Krishnan S | 28.02.2018 | 10:45 AM to 4:00 PM | Second review
58 | Mohana Krishnan S | 01.03.2018 | 10:45 AM to 4:00 PM | Procedure writing | In Progress
59 | Mohana Krishnan S | 02.03.2018 | 10:45 AM to 4:00 PM | Procedure writing | In Progress
60 | Mohana Krishnan S | 03.03.2018 | 10:45 AM to 4:00 PM | Procedure writing | In Progress
|  | Sunday |  | Holiday
61 | Mohana Krishnan S | 05.03.2018 | 10:45 AM to 4:00 PM | Procedure writing | In Progress

## JEYA SUNDARI
NSURE Motor Policy Inssuance System
S.no | Name | Date | Time | Project Task | Status
1 | Jeya Sundari G | 11.12.2017 | 10:45 AM to 4:00 PM | Domain knowledge | Completed
2 | Jeya Sundari G | 12.12.2017 | 10:45 AM to 4:00 PM | Domain knowledge | Completed
3 | Jeya Sundari G | 13.12.2017 | 10:45 AM to 4:00 PM | Refreshing Basics Java | Completed
4 | Jeya Sundari G | 14.12.2017 | 10:45 AM to 4:00 PM | Zeroth Review
5 | Jeya Sundari G | 15.12.2017 | 10:45 AM to 4:00 PM | Installing and Configuring Development Tool | Completed
|  | Saturday |  | Holiday
Sunday
6 | Jeya Sundari G | 18.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Angular JS | Completed
7 | Jeya Sundari G | 19.12.2017 | 10:45 AM to 4:00 PM | Executing Sample Java Project | Completed
8 | Jeya Sundari G | 20.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Spring Framework | Completed
9 | Jeya Sundari G | 21.12.2017 | 10:45 AM to 4:00 PM | Absent
10 | Jeya Sundari G | 22.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
|  | Saturday |  | Holiday
Sunday
Monday
11 | Jeya Sundari G | 26.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
12 | Jeya Sundari G | 27.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
13 | Jeya Sundari G | 28.12.2017 | 10:45 AM to 4:00 PM | Learning Angular Js and Spring Framework | Completed
14 | Jeya Sundari G | 29.12.2017 | 10:45 AM to 4:00 PM | Absent(placement drive)
15 | Jeya Sundari G | 30.12.2017 | 10:45 AM to 4:00 PM | Absent
|  | Sunday |  | Holiday
Monday
16 | Jeya Sundari G | 02.01.2018 | 10:45 AM to 4:00 PM | Grid UI design | Completed
17 | Jeya Sundari G | 03.01.2018 | 10:45 AM to 4:00 PM | UI Design-Module 1 | Completed
18 | Jeya Sundari G | 04.01.2018 | 10:45 AM to 4:00 PM | UI Design-Module 1 | Completed
19 | Jeya Sundari G | 05.01.2018 | 10:45 AM to 4:00 PM | UI Design-Module 1 | Completed
|  | Saturday |  | Holiday
Sunday
20 | Jeya Sundari G | 08.01.2018 | 10:45 AM to 4:00 PM | Absent
21 | Jeya Sundari G | 09.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 1 | Completed
22 | Jeya Sundari G | 10.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 1 | In Progress
23 | Jeya Sundari G | 11.01.2018 | 10:45 AM to 4:00 PM | Dashboard controls | Completed
Holiday
24 | Jeya Sundari G | 17.01.2018 | 10:45 AM to 4:00 PM | Dashboard controls | Completed
25 | Jeya Sundari G | 18.01.2018 | 10:45 AM to 4:00 PM | Dashboard controls | Completed
26 | Jeya Sundari G | 19.01.2018 | 10:45 AM to 4:00 PM | Dashboard controls | In Progress
27 | Jeya Sundari G | 20.01.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
|  | Sunday |  | Holiday
28 | Jeya Sundari G | 22.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 2 | In Progress
29 | Jeya Sundari G | 23.01.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
30 | Jeya Sundari G | 24.01.2018 | 10:45 AM to 4:00 PM | JDBC Connection | Completed
31 | Jeya Sundari G | 25.01.2018 | 10:45 AM to 4:00 PM | JDBC Connection | Completed
|  | Friday |  | Holiday
Saturday
Sunday
32 | Jeya Sundari G | 29.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 2 | Completed
33 | Jeya Sundari G | 30.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 3 | Completed
34 | Jeya Sundari G | 31.01.2018 | 10:45 AM to 4:00 PM | Learning JSON | Completed
35 | Jeya Sundari G | 01.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
36 | Jeya Sundari G | 02.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
37 | Jeya Sundari G | 03.02.2018 | 10:45 AM to 4:00 PM | Absent
|  | Sunday |  | Holiday
38 | Jeya Sundari G | 05.02.2018 | 10:45 AM to 4:00 PM | Learning angular validation | Completed
39 | Jeya Sundari G | 06.02.2018 | 10:45 AM to 4:00 PM | Learning angular validation | Completed
40 | Jeya Sundari G | 07.02.2018 | 10:45 AM to 4:00 PM | Learning angular validation | Completed
41 | Jeya Sundari G | 08.02.2018 | 10:45 AM to 4:00 PM | Angular Js and Form validation | In Progress
42 | Jeya Sundari G | 09.02.2018 | 10:45 AM to 4:00 PM | Angular Js and Form validation | In Progress
43 | Jeya Sundari G | 10.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
|  | Sunday |  | Holiday
44 | Jeya Sundari G | 12.02.2018 | 10:45 AM to 4:00 PM | Angular Js and Form validation | In Progress
45 | Jeya Sundari G | 13.02.2018 | 10:45 AM to 4:00 PM | Angular Js and Form validation | In Progress
46 | Jeya Sundari G | 14.02.2018 | 10:45 AM to 4:00 PM | Angular Js and Form validation | In Progress
47 | Jeya Sundari G | 15.02.2018 | 10:45 AM to 4:00 PM | Angular Js and Form validation | In Progress
48 | Jeya Sundari G | 16.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
49 | Jeya Sundari G | 17.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
Sunday
50 | Jeya Sundari G | 19.02.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
51 | Jeya Sundari G | 20.02.2018 | 10:45 AM to 4:00 PM | Angular Js and Form validation | In Progress
52 | Jeya Sundari G | 21.02.2018 | 10:45 AM to 4:00 PM | Angular Js and Form validation | In Progress
53 | Jeya Sundari G | 22.02.2018 | 10:45 AM to 4:00 PM | Angular Js and Form validation | In Progress
54 | Jeya Sundari G | 23.02.2018 | 10:45 AM to 4:00 PM | Angular Js and Form validation | In Progress
|  | Saturday |  | Holiday
Sunday
55 | Jeya Sundari G | 26.02.2018 | 10:45 AM to 4:00 PM | UI grid | In Progress
56 | Jeya Sundari G | 27.02.2018 | 10:45 AM to 4:00 PM | Second review
57 | Jeya Sundari G | 28.02.2018 | 10:45 AM to 4:00 PM | Second review
58 | Jeya Sundari G | 01.03.2018 | 10:45 AM to 4:00 PM | Module 2 Ui grid | In Progress
59 | Jeya Sundari G | 02.03.2018 | 10:45 AM to 4:00 PM | Module 2 Ui grid | In Progress
60 | Jeya Sundari G | 03.03.2018 | 10:45 AM to 4:00 PM | Module 2 Ui grid | In Progress
|  | Sunday |  | Holiday
61 | Jeya Sundari G | 05.03.2018 | 10:45 AM to 4:00 PM | Database table creation | In Progress